## Agile Product Backlog
PRODUCT BACKLOG
ID | USER STORY | SPRINT # | ASSIGNED TO | START | FINISH | PRIORITY | COMPLEXITY | RETURN ON INVESTMENT | STATUS
1 | Aa a user, I can search based on code | 1 | Neja | 29th Jan | 30th Jan | 9 | 1 | 9 | Completed
2 | As a user, I can search based on procedure/condition | 1 | Neja | 30th Jan | 30th Jan | 10 | 1 | 10 | Completed | Completed
3 | As a user, I can search based on live location | 2 | Ross | 3rd Feb |  | 7 | 5 | 1 | In Progress | Not Started
4 | As a user, I can search based on location input | 2 | Ross | 5th Feb | 7th Feb | 8 | 3 | 3 | Completed | In Progress
5 | As a user, I can search based on a description of a procedure/condition | 2 | Neja, Kayla | 4th Feb | 5th Feb | 6 | 2 | 3 | Completed
6 | As a user, I can order the search results based on price | 1 | Stas | 26th Jan | 27th Jan | 8 | 1 | 8 | Completed
7 | As a user, I can order the search results based on distance | 1 | Stas | 26th Jan | 27th Jan | 8 | 1 | 8 | Completed
8 | As a user, I can view the output of a search as a list | 1 | Stephen | 27th Jan | 30th Jan | 10 | 3 | 3 | Completed
9 | As a user, I can view the search results on a map | 2 | Ross | 3rd Feb | 6th Feb | 5 | 8 | 1 | Completed
10 | As a user, I can see the price information on a marker for each result on the map | 2 | Kamila, Kayla | 4th Feb | 5th Feb | 4 | 5 | 1 | Completed
11 | As a programmer, I want to find an API to support Google Maps for live location services | 1 | Ross | 27th Jan | 29th Jan | 7 | 5 | 1 | Completed
12 | As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user | 1 | Kamila | 27th Jan | 28th Jan | 10 | 6 | 2 | Completed
13 | As a user, I can set a price range for the search | 1 | Stephen | 28th Jan | 31st Jan | 2 | 2 | 1 | Completed
14 | As a user, I can set a distance range for the search | 1 | Stas | 27th Jan | 30th Jan | 3 | 3 | 1 | Completed
15 | As a user, I can order the search results based on the ranking which is a combination of price and distance | 2 | Neja | 6th Feb |  | 4 | 5 | 1 | In Progress
16 | As a user, I can navigate with a keyboard | 2 | Stas, Stephen | 6th Feb | 6th Feb | 3 | 1 | 3 | Completed
17 | As a user can view the data regardless of colour blindness | 2 | Stas, Stephen | 6th Feb | 6th Feb | 3 | 2 | 2 | Completed
18 | As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data | 1 | Kayla | 27th Jan | 31st Jan | 10 | 5 | 2 | Completed
19 | As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | 1 | Kamila | 27th Jan | 6th Feb | 10 | 7 | 1 | Completed
20 | As a programmer, I want to store longtitude/latitude coordinates for each hospital address in the database a this allows for quicker fetches | 2 | Kamila | 3rd Feb | 5th Feb | 4 | 3 | 1 | Completed
21 | As a programmer, I would like to optimise a webpage based on user feedback | 2 | Kayla | 3rd Feb | 7th Feb | 8 | 5 | 2 | Completed
| As a programmer, I want to host the website on the server | 2 | Neja | 3rd Feb | 5th Feb | 10 | 5 | 2 | Completed
23 | As a programmer, I want to create unit tests for all existing functionality so that I can ensure further development doesn't break any existing code | 2 | Stas | 3rd Feb | 7th Feb | 10 | 5 | 2 | Completed
24 | As a purchaser, I can delete data from the existing data set | n/a |  |  |  | 1 |  |  | Not Started
25 | As a purchaser, I can load new data from the existing data set | n/a |  |  |  | 1 |  |  | Not Started
26 | As a purchaser, I can update existing data | n/a |  |  |  | 1 |  |  | Not Started
27 | As a purchaser, I can add data to the existing data set | n/a |  |  |  | 1 |  |  | Not Started