## Agile Sprint 2 Backlog
SPRINT BACKLOG - SPRINT 2
ID | TASK | STATUS | ASSIGNED TO | COMPLETED BY | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1 | As a user, I can search based on location input | Completed | Ross | Kamila, Kayla | 8 | 3 | 3 | 3 | 2 | -2 | -3
2 | As a user, I can search based on live location | In progress | Ross | n/a | 7 | 5 | 5 | 4 | 3 | 2 | 1
3 | As a user, I can search based on a description of a procedure | Completed | Neja, Kayla | Kayla, Kamila | 6 | 2 | 2 | 0 | 0 | 0 | 0
4 | As a user, I can view the search results on a map | Completed | Ross | Ross | 5 | 8 | 7 | 5 | 3 | 1 | 0
5 | As a programmer, I want to store longtitude/latitude coordinates for each hospital address in the database a this allows for quicker fetches | Completed | Kamila | Kamila | 4 | 3 | 1 | 1 | 0 | 0 | 0
6 | As a user, I can see the price information on a marker for each result on the map | Completed | Ross | Ross | 4 | 5 | 5 | 5 | 0 | 0 | 0
7 | As a user, I can order the search results based on the ranking which is a combination of price, distance | In progress | Neja | Neja | 4 | 5 | 5 | 5 | 4 | 4 | 4
8 | As a user, I can navigate with a keyboard | Completed | Stephen | Neja | 3 | 1 | 1 | 1 | 1 | 0 | 0
9 | As a user, I can view the data regardless of colour blindness | Completed | Stephen | Neja | 3 | 2 | 2 | 2 | 2 | 0 | 0
10 | As a programmer, I would like to optimise a webpage based on user feedback | Completed | Kayla | Kayla, Neja | 8 | 5 | 5 | 4 | 2 | 1 | 0
11 | As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | Completed | Neja, Kamila | Neja, Kamila | 10 | 3 | 2 | 2 | 1 | 1 | 0
12 | As a programmer, I want to create unit tests for all existing functionality so that I can ensure further development doesn't break any existing code | Completed | Stas | Stas | 10 | 5 | 4 | 3 | 2 | 1 | 0
13 | As a programmer, I want to host the website on the server | Completed | Neja | Neja | 10 | 5 | 4 | 1 | 1 | 1 | 0
| TOTAL |  |  |  |  | 52 | 46 | 36 | 21 | 11 | 5 | 5

## Detailed Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | ASSIGNED TO | COMPLETED BY | STATUS | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
As a user, I can search based on live location | Ross | n/a | In progress | 7 | 5 | 5 | 3 | 2 | 1 | 1
Use Goggle API to establish a users location |  |  |  |  | 5 | 5 | 3 | 2 | 1 | 1
As a user, I can search based on location input | Ross | Kamila, Kayla | Completed | 8 | 3 | 3 | 3 | 2 | -2 | -3
Convert ZIP code entered by the user into a longitude and latitude |  |  |  |  | 3 | 3 | 3 | 2 | -2 | -3
Implement the haversine formula to calculate the distance |  |  |  |  | 3 | 3 | 3 | 3 | -2 | -3
Edit the Query.java class to take a distance parameter (inc. adding getters and setters) |  |  |  |  | 3 | 3 | 3 | 3 | -2 | -3
Include the distance parameter in the creating of the table on the results page |  |  |  |  | 3 | 3 | 3 | 3 | -2 | -3
Ensure this distance parameter is also passed through to the maps part of the code to ensure each hospital is related to the distance shown on the map |  |  |  |  | 3 | 3 | 3 | 3 | -2 | -3
As a user, I can search based on a description of a procedure | Neja, Kayla | Kayla, Kamila | Completed | 6 | 2 | 2 | 0 | 0 | 0 | 0
Split users input by word |  |  |  |  | 2 | 2 | 0 | 0 | 0 | 0
Pick out keywords within their search |  |  |  |  | 2 | 2 | 0 | 0 | 0 | 0
Implement the query to take a variable amount of parameters (depending on the number of keywords picked out) |  |  |  |  | 2 | 2 | 0 | 0 | 0 | 0
As a user, I can view the search results on a map | Ross | Ross | Completed | 5 | 8 | 7 | 5 | 3 | 1 | 0
Drop pins accuratly on the google map |  |  |  |  | 2 | 1 | 0 | 0 | 0 | 0
Info Boxes to be displayed on the mpap |  |  |  |  | 2 | 2 | 1 | 0 | 0 | 0
When results table clicked display the marker |  |  |  |  | 2 | 2 | 2 | 2 | 1 | 0
When marker clicked highlight result table row |  |  |  |  | 2 | 2 | 2 | 2 | 1 | 0
As a programmer, I want to store longtitude/latitude coordinates for each hospital address in the database a this allows for quicker fetches | Kamila | Kamila | Completed | 4 | 3 | 1 | 1 | 0 | 0 | 0
Make a new database table |  |  |  |  | 3 | 1 | 1 | 0 | 0 | 0
Import all the ZIP codes, longitudes, latitudes and provider IDs to the table |  |  |  |  | 3 | 1 | 1 | 0 | 0 | 0
As a user, I can see the price information on a marker for each result on the map | Ross | Ross | Completed | 4 | 5 | 5 | 5 | 0 | 0 | 0
Establish an info window for eahc marker |  |  |  |  | 2 | 1 | 0 | 0 | 0 | 0
Pass price information to the info window |  |  |  |  | 3 | 2 | 1 | 0 | 0 | 0
As a user, I can order the search results based on the ranking which is a combination of price, distance | Neja | Neja | In progress | 4 | 5 | 5 | 5 | 4 | 4 | 4
Create an algorithm for ranking |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 0
Display ranking in the table |  |  |  |  | 2 | 2 | 2 | 1 | 1 | 1
Sort by ranking |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2
As a user, I can navigate with a keyboard | Stephen | Neja | Completed | 3 | 1 | 1 | 1 | 1 | 0 | 0
Test if the form can be navigated with a keyboard |  |  |  |  | 1 | 1 | 1 | 1 | 0 | 0
As a user, I can view the data regardless of colour blindness | Stephen | Neja | Completed | 3 | 2 | 2 | 2 | 2 | 0 | 0
Test with colour blindness filter on https://www.toptal.com/designers/colorfilter |  |  |  |  | 2 | 2 | 2 | 2 | 0 | 0
As a programmer, I would like to optimise a webpage based on user feedback | Kayla | Kayla, Neja | Completed | 8 | 5 | 5 | 4 | 2 | 1 | 0
Edit the table of results to show only necessary information |  |  |  |  | 5 | 5 | 4 | 2 | 1 | 0
Discard 'minimum distance' input box |  |  |  |  | 5 | 0 | 0 | 0 | 0 | 0
Make any accessibility changes necessary |  |  |  |  | 5 | 5 | 4 | 2 | 1 | 0
As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | Neja, Kamila | Neja, Kamila | Completed | 10 | 3 | 2 | 2 | 1 | 1 | 0
Continue implementing new functions while making sure everything is working |  |  |  |  | 3 | 2 | 2 | 1 | 1 | 0
As a programmer, I want to create unit tests for all existing functionality so that I can ensure further development doesn't break any existing code | Stas | Stas | Completed | 10 | 5 | 4 | 3 | 2 | 1 | 0
Write unit tests for algorithms to test each programmers individual tests |  |  |  |  | 5 | 4 | 3 | 2 | 1 | 0
As a programmer, I want to host the website on the server | Neja | Neja | Completed | 10 | 5 | 4 | 1 | 1 | 1 | 0
Deploy on Azure servers |  |  |  |  | 5 | 4 | 1 | 1 | 1 | 0
TOTAL |  |  |  |  | 133 | 106 | 82 | 54 | 9 | 9 | 0