## Agile Sprint 1 Backlog
SPRINT BACKLOG - SPRINT 1
ID | USER STORIES/TASKS | STATUS | ASSIGNED TO | COMPLETED BY | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1 | A user can search based on code | Completed | Neja | Neja | 9 | 1 | 1 | 1 | 1 | 0 | 0
2 | A user can search based on procedure/condition | Completed | Neja | Neja | 10 | 1 | 1 | 1 | 3 | 3 | 0
3 | A user can view results in a map | Completed | Ross | Ross | 9 | 4 | 4 | 3 | 2 | 1 | 0
4 | A user can order the search results based on price | Completed | Stas | Stas | 8 | 1 | 1 | 0 | 0 | 0 | 0
5 | A user can order the search results based on distance | Completed | Stas | Stas | 8 | 1 | 1 | 1 | 0 | 0 | 0
6 | A user can view the output of a search as a list | Completed | Stephen | Stephen | 10 | 3 | 2 | 1 | 0 | 0 | 0
7 | As a programmer, I want to find an API to support Google Maps for live location services | Completed | Ross | Ross | 7 | 5 | 2 | 0 | 0 | 0 | 0
8 | As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user | Completed | Kamila | Kamila | 10 | 6 | 3 | 0 | 0 | 0 | 0
9 | A user can set a price range for their search | Completed | Stephen | Stephen | 2 | 2 | 2 | 1 | 1 | 0 | 0
10 | A user can set a distance range for their search | Completed | Stas | Stas | 3 | 3 | 3 | 2 | 1 | 0 | 0
11 | As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data | Completed | Kayla | Kayla | 10 | 5 | 3 | 1 | 0 | 0 | 0
12 | As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience | In progress |  | Kamila, Kayla, Neja | 10 | 7 | 7 | 7 | 5 | 3 | 3
| TOTAL |  |  |  |  | 39 | 30 | 18 | 13 | 7 | 3 | 0

## Detailed Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | ASSIGNED TO | COMPLETED BY | STATUS | PRIORITY | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
A user can search based on code | Neja | Neja | Completed | 9 | 1 | 3 | 3 | 2 | 1 | 0
Write SQL Query |  | Neja |  |  | 1 | 1 | 0 | 0 | 0 | 0
Parse information from the input form to JSP file |  | Neja |  |  | 1 | 1 | 1 | 1 | 0 | 0
Call Java functions with selected parameters and query |  | Neja |  |  | 1 | 1 | 1 | 3 | 3 | 0
A user can search based on condition/procedure | Neja | Neja | Completed | 10 | 1 | 3 | 3 | 3 | 2 | 0
Write SQL Query |  | Neja |  |  | 1 | 1 | 0 | 0 | 0 | 0
Parse information from the input form to JSP file |  | Neja |  |  | 1 | 1 | 1 | 1 | 0 | 0
Call Java functions with selected parameters and query |  | Neja |  |  | 1 | 1 | 1 | 3 | 3 | 0
A user can view results in a map | Ross | Ross | Completed | 9 | 4 | 3 | 2 | 1 | 0 | 0
Creating a search funtion |  | Ross |  |  | 2 | 2 | 1 | 0 | 0 | 0
Function tailored to being able to search by location |  | Ross |  |  | 2 | 2 | 2 | 1 | 0
A user can order the search results based on price | Stas | Stas | Completed | 8 | 1 | 1 | 0 | 0 | 0 | 0
Created the search funtion |  | Stas |  |  | 1 | 1 | 0 | 0 | 0 | 0
A user can order the search results based on distance | Stas | Stas | Completed | 8 | 1 | 1 | 1 | 0 | 0 | 0
Created a quick sort in java to sort search results |  | Stas |  |  | 1 | 1 | 1 | 0 | 0 | 0
A user can view the output of a search as a list | Stephen | Stephen | Completed | 10 | 3 | 2 | 1 | 0 | 0 | 0
Search returns a formatted list of all results |  | Stephen |  | 2 | 2 | 2 | 2 | 2 | 2 | 0
As a programmer, I want to find an API to support Google Maps for live location services | Ross | Ross | Completed | 7 | 5 | 2 | 0 | 0 | 0 | 0
Google Api Asks for permission before using location |  | Ross |  |  | 3 | 3 | 0 | 0 | 0 | 0
google uses cell towers to triangulate loation |  | Ross |  |  | 2 | 2 | 0 | 0 | 0 | 0
As a programmer, I want the data to be stored in a database so that all the data is easy to access for any user | Kamila | Kamila | Completed | 10 | 6 | 3 | 0 | 0 | 0 | 0
create Database for holding information |  | Kamila |  |  | 3 | 3 | 0 | 0 | 0 | 0
Input information into database |  | Kamila |  |  | 3 | 3 | 3 | 0 | 0 | 0
A user can set a price range for their search | Stephen | Stephen | Completed | 2 | 2 | 2 | 2 | 1 | 1 | 0
Searches based on the range of the user input |  | Stephen |  |  | 2 | 2 | 2 | 1 | 1 | 0
A user can set a distance range for their search | Stas | Stas | Completed | 3 | 3 | 3 | 2 | 1 | 0 | 0
Created a quick sort that has a min and max for range |  | Stas |  |  | 3 | 3 | 2 | 1 | 0 | 0
As a programmer, I would like to create a webpage as the main interface to allow the user easy and effective access to all the data | Kayla | Kayla | Completed | 10 | 5 | 3 | 1 | 0 | 0 | 0
Create basic home page |  | Kayla |  |  | 2 | 2 | 0 | 0 | 0 | 0
Create results page for search results |  | Kayla |  |  | 1 | 1 | 1 | 0 | 0 | 0
Edit CSS |  | Kayla |  |  | 1 | 1 | 1 | 1 | 0 | 0
Write input validation |  | Kayla |  |  | 1 | 1 | 1 | 1 | 0 | 0
As a programmer, I want to integrate the database, backend and frontend to allaw the user a seamless experience |  |  | In Progress | 10 | 7 | 9 | 9 | 7 | 5 | 1
Connecting Java backend to the database (JDBC Driver) |  | Kamila, Neja |  |  | 3 | 3 | 3 | 3 | 0 | 0
Connecting JSP to the Java backend |  | Kamila |  |  | 2 | 2 | 2 | 2 | 2 | 0
Connecting HTML to JSP |  | Kamila, Kayla |  |  | 1 | 1 | 1 | 1 | 1 | 0
Adding CSS and JS to the webiste |  | Kamila, Kayla |  |  | 2 | 2 | 2 | 2 | 2 | 1
Connecting to the server (Apache Tomcat) |  | Kamila, Neja |  |  | 1 | 1 | 1 | 1 | 0 | 0